## February
CMS Fusion
Date | Topic | Status | Queries | Reference
|  |  |  | Document | Videos/Requirement
2018-02-01 | Business Overview | Complete |  |  | Equifax Business Overview and Intro to Credit Data
2018-02-02 | Data Sources | Complete |  |  | Intro to Other Data Sources
2018-02-03 | WEEKEND
2018-02-04 | WEEKEND
2018-02-05 | Technology stack in MI, D36 | Complete |  |  | Intro to the Technology stack in MI, D36, Part 3
2018-02-06 | CMS Fusion Introduction | Complete |  | 1.CMS Fusion Introduction | Rams_Explanation_on_Fusion_ppt-20171020 1241-1
2018-02-07 | Input Process | Complete | how are converting the EBCDIC code to ASCII, how to we deal in automation of these data coming in input | 2. Input Process - v2.0 | Input_SourceMatch_DataMenu-20171020 1317-2
2018-02-08 | Source Match Process | Complete |  | 3.Source Match Process | Input_SourceMatch_DataMenu-20171020 1317-2
2018-02-09 | Data Menu Functional | Complete |  | 4.Data Menu Functional Overview-v2.0 | Input_SourceMatch_DataMenu-20171020 1317-2
2018-02-10 | WEEKEND
2018-02-11 | WEEKEND
2018-02-12 |  |  |  | 4.Data Menu Functional Overview-v2.0
2018-02-13 | Refinement Process | Complete |  | 5.Refinement Process | John_Reporting_Refinement
2018-02-14 | Data Processing | Complete |  | 6.Data Processing | John_Reporting_DataProcessing
Karthik Demo on Running the Jobs Till Data Processing
2018-02-15 | Output Process | Complete |  | 7.Output Process | John_Output and Jobstacking-20171024 1246-1
Karthik Demo on Running the Jobs Till Data Processing
2018-02-16 | All Documents | Review
2018-02-17 | WEEKEND
2018-02-18 | WEEKEND
2018-02-19 | Job Stacking | Complete |  | 8.Job Stacking | Karthik_Output_jobstackings-JobRun Demo-20171024 1752-1
| Operations | Complete | Differentiate usage of Active/Inactive Button | 12.Operations | John_Output and Jobstacking-20171024 1246-1
Ram_Operations and JobStacking-20171024 1457-2
2018-02-20 | Job XML and JET | Not Done | No documentation and proper recording is available | Job XML and JET | Ram_JET_JobXML-20171026 1259-1
2018-02-21 | Audit | Complete |  | 13.Audit | John_Prasad_Audit -20171027 1315-2
2018-02-22 | Shipping | Complete |  | 9. Shipping
2018-02-23 | QC | Complete |  | 10. QC
| Seibel | Complete |  |  | Ram_Siebel-20171027 1246-1
2018-02-24 | WEEKEND
2018-02-25 | WEEKEND
2018-02-26 | Sprint58(CF2-2351) | Done |  | Input Process(Functional Document) | Carriage Return and Line Feed Issues with File Import
2018-02-27 | Sprint58(CF2-2621) | Done |  | Fusion-Input-TechnicalDocv1.1 | System does not display error w.r.t Length validations for the DOB,DOB delimited and similar Date related fields
2018-02-28 | Sprint58(CF2-1112) | Done |  | Input Process(Functional Document) | MLA Transaction ID layout validation
| Sprint58(CF2-315) | Done |  | 4. Data Menu Functional Overview-v2.0 | Add Warnings to GP_LOAD stat for empty files and Zero Accept Records
Repository Link: | \\atleisfile1\CMS Fusion IT\Transition\Fusion App Functional\Documentation\Varnika

## March
CMS Fusion
Date | Topic | Status | Queries | Reference
|  |  |  | Document | Requirement
2018-03-01 | Sprint58(CF2-2822) | Done |  | Document updation is not required | Add Condition Operator of "IN" and "Not IN"
| Sprint58(CF2-289) | Done |  | 7. Output Process | No fast forward and backward button on Output Record type screen.
2018-03-02 | Sprint58(CF2-2655) | Done |  | 7. Output Process | Regression Automation Updates - Output Process
2018-03-03 | WEEKEND
2018-03-04 | WEEKEND
2018-03-05 | Sprint58(CF2-299) | Done |  | Document updation is not required | QC Tab enhancement
| Sprint58(CF2-2910) | Done | Text on the Button does not match the Requirement | 4. Data Menu Functional Overview-v2.0 | Data Menu - (UI) - preliminary support for ANav modules on Datapump 2.0
2018-03-06 | Sprint59(CF2-320) | Done |  | 4. Data Menu Functional Overview-v2.0 | FACT Act Defaults with popup enhancement
| Sprint59(CF2-305) | Done |  | 4. Data Menu Functional Overview-v2.0 | Sample Files need to replicate Data Sources
| Sprint59(CF2-3100) | Done |  | Document updation is not required | Ability to compare two different DM process configuration's
| Sprint59(CF2-2574) | Done |  | Input Process(Functional Document) | File Import-support for selecting a File Tokenization process as an input
2018-03-07 | Sprint59(CF2-3016) | Done |  | Document updation is not required | Enhancing the Cancel Behavior for GP Work Items
| Sprint59(CF2-2966) | Done |  | Document updation is not required | Change Fusion to use Predicted information only for Loading to GP
2018-03-08 | Sprint59(CF2-3047) | Done |  | Document updation is not required | Ensure that the selected input is valid for the selected json configuration
| Sprint59(CF2-3045) | Done |  | Document updation is not required | FFF_GPEXPORT (Generate Data Menu source file)
| Sprint59(CF2-3046) | Done |  | Document updation is not required | QA-FFF - Generate JOB XML for FFF with Model and/or DA segments
| Sprint59(CF2-3024) | Done |  | 4. Data Menu Functional Overview-v2.0 | Consolidate the first 4 datamenu pages to 1 page
2018-03-09 | Sprint59(CF2-3026) | Done |  | 4. Data Menu Functional Overview-v2.0 | JET XML allow to save on local machine/CopyToClipboard
| Sprint59(CF2-3141) | Done |  | Document updation is not required | Remove "N" from the source dropdown of DEStd page in DM, when choosing to use the same option for all levels.
| Sprint59(CF2-3148) | Done |  | Document updation is not required | Resolving Broken Test cases in suite during Regression-QA4_2017
| Sprint59(CF2-3218) | Done |  | Document updation is not required | Error message gets displayed multiple times on clicking continue button multiple times on DE Standards
| Sprint59(CF2-3242) | Done |  | Document updation is not required | Workitem level, View statistics link should directly display the errors/warnings tab
| Sprint60(CF2-2375) | Done |  | 2. Input Process - v2.0 | Source File Size Exceeds Fusions Capacities
2018-03-10 | WEEKEND
2018-03-11 | WEEKEND
2018-03-12 | Sprint60(CF2-3135) | Done |  | 11.Reporting, Inquiry posting | Inquiry Posting - add MLA ID to inqpost input file
| Sprint60(CF2-3136) | Done |  | 4. Data Menu Functional Overview-v2.0 | Data Menu - Summary's layout view must display Predicted Data Type
| Sprint60(CF2-3145) | Done |  | Document updation is not required | Ability to set the NAS Root Location per project
| Sprint60(CF2-3226) | Done |  | 4. Data Menu Functional Overview-v2.0 | Enhancing existing Datamenu Summary Job xml page to pop up window
2018-03-13 | Sprint60(CF2-3229) | Done |  | Input Process(Functional Document) | File Tokenization - Record Length Validation of Tokenized File
| Sprint60(CF2-3286) |  |  |  | Prevent multiple clicks on toolbar buttons in the output layout grid until the current operation is completed
| Sprint60(CF2-3417) | Done |  | 6. Data Processing | Match Join - Stats update test - POC
2018-03-14
2018-03-15
2018-03-16
2018-03-17
2018-03-18
2018-03-19 | Input Dependency
2018-03-20
2018-03-21
2018-03-22
2018-03-23
2018-03-24
2018-03-25
2018-03-26
2018-03-27
2018-03-28
2018-03-29
2018-03-30
2018-03-31

## Sheet2
Process_Output | SubProcess | Process_Input | Condition | Mandatory
files in the nas location |  | Input Process | no tokenization |  | address, FirstName,LastName
files in the nas location |  | Reporting | ExecuteSAS
InputProcess |  | SourceMatch
InputProcess |  | DataMenu | CID
InputProcess |  | Refinement
InputProcess |  | DataProcessing | DNS
InputProcess |  | DataProcessing | RandomNth
InputProcess |  | DataProcessing | full file Fixed
InputProcess |  | DataProcessing | filtering
InputProcess |  | DataProcessing | MathJoin | MASTERFILE
InputProcess |  | DataProcessing | MathJoin | Matchfile
InputProcess |  | DataProcessing | MLAStandalone
InputProcess |  | Output
InputProcess |  | Reporting | QuickfreqReport
InputProcess |  | Reporting | ProjectStats
InputProcess |  | Audit | SampleFile
InputProcess |  | Audit | DataCompare
InputProcess |  | Inquiry Posting | NetDown
SourceMatch |  | SourceMatch
SourceMatch |  | DataMenu | ListSource
SourceMatch |  | DataMenu | CID
SourceMatch |  | Refinement
SourceMatch |  | DataProcessing | DNS
SourceMatch |  | DataProcessing | RandomNth
SourceMatch |  | DataProcessing | full file Fixed
SourceMatch |  | DataProcessing | filtering
SourceMatch |  | DataProcessing | MathJoin | MASTERFILE
SourceMatch |  | DataProcessing | MathJoin | Matchfile
SourceMatch |  | Output
SourceMatch |  | Reporting | QuickfreqReport
SourceMatch |  | Reporting | ProjectStats
SourceMatch |  | Audit | SampleFile
SourceMatch |  | Audit | DataCompare
DataMenu |  | SourceMatch
DataMenu |  | DataMenu | CID
DataMenu |  | Refinement
DataMenu |  | DataProcessing | DNS
DataMenu |  | DataProcessing | RandomNth
DataMenu |  | DataProcessing | full file Fixed
DataMenu |  | DataProcessing | filtering
DataMenu |  | DataProcessing | MathJoin | MASTERFILE
DataMenu |  | DataProcessing | MathJoin | Matchfile
DataMenu |  | Output
DataMenu |  | Reporting | QuickfreqReport
DataMenu |  | Reporting | StandardReportPackage
DataMenu |  | Reporting | ProjectStats
DataMenu |  | Reporting | FICOReport
DataMenu |  | Audit | SampleFile
DataMenu |  | Audit | DataCompare
DataMenuE |  | SourceMatch
DataMenuE |  | DataMenu | CID
DataMenuE |  | Refinement
DataMenuE |  | DataProcessing | RandomNth
DataMenuE |  | DataProcessing | full file Fixed
DataMenuE |  | DataProcessing | filtering
DataMenuE |  | DataProcessing | MathJoin | Matchfile
DataMenuE |  | Output
DataMenuE |  | Reporting | QuickfreqReport
DataMenuE |  | Reporting | StandardReportPackage
DataMenuE |  | Reporting | ProjectStats
DataMenuE |  | Reporting | FICOReport
DataMenuE |  | Audit | SampleFile
DataMenuE |  | Audit | DataCompare
Refinement |  | SourceMatch
Refinement |  | DataMenu | CID
Refinement |  | Refinement
Refinement |  | DataProcessing | DNS
Refinement |  | DataProcessing | RandomNth
Refinement |  | DataProcessing | full file Fixed
Refinement |  | DataProcessing | filtering
Refinement |  | DataProcessing | MathJoin | MASTERFILE
Refinement |  | DataProcessing | MathJoin | Matchfile
Refinement |  | Output
Refinement |  | Reporting | QuickfreqReport
Refinement |  | Reporting | StandardReportPackage
Refinement |  | Reporting | ProjectStats
Refinement |  | Audit | SampleFile
Refinement |  | Audit | DataCompare
DataProcessing | DoNotSolicit | SourceMatch
DataProcessing | DoNotSolicit | DataMenu | CID
DataProcessing | DoNotSolicit | Refinement
DataProcessing | DoNotSolicit | DataProcessing | DNS
DataProcessing | DoNotSolicit | DataProcessing | RandomNth
DataProcessing | DoNotSolicit | DataProcessing | full file Fixed
DataProcessing | DoNotSolicit | DataProcessing | filtering
DataProcessing | DoNotSolicit | DataProcessing | MathJoin | MASTERFILE
DataProcessing | DoNotSolicit | DataProcessing | MathJoin | Matchfile
DataProcessing | DoNotSolicit | Output
DataProcessing | DoNotSolicit | Reporting | QuickfreqReport
DataProcessing | DoNotSolicit | Reporting | StandardReportPackage
DataProcessing | DoNotSolicit | Reporting | ProjectStats
DataProcessing | DoNotSolicit | Audit | SampleFile
DataProcessing | DoNotSolicit | Audit | DataCompare
DataProcessing | RandomNth | SourceMatch
DataProcessing | RandomNth | DataMenu | CID
DataProcessing | RandomNth | Refinement
DataProcessing | RandomNth | DataProcessing | DNS
DataProcessing | RandomNth | DataProcessing | RandomNth
DataProcessing | RandomNth | DataProcessing | full file Fixed
DataProcessing | RandomNth | DataProcessing | filtering
DataProcessing | RandomNth | DataProcessing | MathJoin | MASTERFILE
DataProcessing | RandomNth | DataProcessing | MathJoin | Matchfile
DataProcessing | RandomNth | Output
DataProcessing | RandomNth | Reporting | QuickfreqReport
DataProcessing | RandomNth | Reporting | StandardReportPackage
DataProcessing | RandomNth | Reporting | ProjectStats
DataProcessing | RandomNth | Audit | SampleFile
DataProcessing | RandomNth | Audit | DataCompare
DataProcessing | FFF | SourceMatch
DataProcessing | FFF | DataMenu | CID
DataProcessing | FFF | Reporting | ProjectStats
DataProcessing | Filter | SourceMatch
DataProcessing | Filter | DataMenu | CID
DataProcessing | Filter | Refinement
DataProcessing | Filter | DataProcessing | DNS
DataProcessing | Filter | DataProcessing | RandomNth
DataProcessing | Filter | DataProcessing | full file Fixed
DataProcessing | Filter | DataProcessing | filtering
DataProcessing | Filter | DataProcessing | MathJoin | MASTERFILE
DataProcessing | Filter | DataProcessing | MathJoin | Matchfile
DataProcessing | Filter | Output
DataProcessing | Filter | Reporting | QuickfreqReport
DataProcessing | Filter | Reporting | StandardReportPackage
DataProcessing | Filter | Reporting | ProjectStats
DataProcessing | Filter | Audit | SampleFile
DataProcessing | Filter | Audit | DataCompare
DataProcessing | Math Join | SourceMatch
DataProcessing | Math Join | DataMenu | CID
DataProcessing | Math Join | Refinement
DataProcessing | Math Join | DataProcessing | DNS
DataProcessing | Math Join | DataProcessing | RandomNth
DataProcessing | Math Join | DataProcessing | full file Fixed
DataProcessing | Math Join | DataProcessing | filtering
DataProcessing | Math Join | DataProcessing | MathJoin | MASTERFILE
DataProcessing | Math Join | DataProcessing | MathJoin | Matchfile
DataProcessing | Math Join | Output
DataProcessing | Math Join | Reporting | QuickfreqReport
DataProcessing | Math Join | Reporting | StandardReportPackage
DataProcessing | Math Join | Reporting | ProjectStats
DataProcessing | Math Join | Audit | SampleFile
DataProcessing | Math Join | Audit | DataCompare
DataProcessing | RollingSupression | SourceMatch
DataProcessing | RollingSupression | DataMenu | CID
DataProcessing | RollingSupression | Refinement
DataProcessing | RollingSupression | DataProcessing | DNS
DataProcessing | RollingSupression | DataProcessing | RandomNth
DataProcessing | RollingSupression | DataProcessing | full file Fixed
DataProcessing | RollingSupression | DataProcessing | filtering
DataProcessing | RollingSupression | DataProcessing | MathJoin | MASTERFILE
DataProcessing | RollingSupression | DataProcessing | MathJoin | Matchfile
DataProcessing | RollingSupression | Output
DataProcessing | RollingSupression | Reporting | QuickfreqReport
DataProcessing | RollingSupression | Reporting | ProjectStats
DataProcessing | RollingSupression | Audit | SampleFile
DataProcessing | RollingSupression | Audit | DataCompare
Output |  | SourceMatch
Output |  | DataMenu | CID
Output |  | Refinement
Output |  | DataProcessing | DNS
Output |  | DataProcessing | RandomNth
Output |  | DataProcessing | full file Fixed
Output |  | DataProcessing | filtering
Output |  | DataProcessing | MathJoin | MASTERFILE
Output |  | DataProcessing | MathJoin | Matchfile
Output |  | Output
Output |  | Reporting | QuickfreqReport
Output |  | Reporting | StandardReportPackage
Output |  | Reporting | ProjectStats
Output |  | Audit | SampleFile
Output |  | Audit | DataCompare
Output |  | Shipping | completed job
Output |  | Shipping | predicted output
Reporting | SASProcess | SourceMatch
Reporting | SASProcess | DataMenu | CID
Reporting | SASProcess | Reporting | ProjectStats
Reporting | SASProcess | Shipping | predicted output
Reporting | QuickFreqReport | SourceMatch
Reporting | QuickFreqReport | DataMenu | CID
Reporting | QuickFreqReport | Reporting | ProjectStats
Reporting | QuickFreqReport | Shipping | completed job
Reporting | QuickFreqReport | Shipping | predicted output
Reporting | StandardReportPackage | SourceMatch
Reporting | StandardReportPackage | DataMenu | CID
Reporting | StandardReportPackage | Reporting | ProjectStats
Reporting | StandardReportPackage | Shipping | completed job
Reporting | StandardReportPackage | Shipping | predicted output
Reporting | FICO Report | SourceMatch
Reporting | FICO Report | DataMenu | CID
Reporting | FICO Report | Reporting | ProjectStats
Reporting | FICO Report | Shipping | completed job
Reporting | FICO Report | Shipping | predicted output
Audit | AuditSampleFile | SourceMatch
Audit | AuditSampleFile | DataMenu | CID
Audit | AuditSampleFile | Refinement
Audit | AuditSampleFile | DataProcessing | DNS
Audit | AuditSampleFile | DataProcessing | RandomNth
Audit | AuditSampleFile | DataProcessing | full file Fixed
Audit | AuditSampleFile | DataProcessing | filtering
Audit | AuditSampleFile | DataProcessing | MathJoin | MASTERFILE
Audit | AuditSampleFile | DataProcessing | MathJoin | Matchfile
Audit | AuditSampleFile | Output
Audit | AuditSampleFile | Reporting | QuickfreqReport
Audit | AuditSampleFile | Reporting | ProjectStats
Audit | AuditSampleFile | Audit | SampleFile
Audit | AuditSampleFile | Audit | DataCompare
Audit | AuditSampleFile | Shipping | completed job
Audit | AuditSampleFile | Shipping | predicted output
Audit | AuditCompare | SourceMatch |  |  | address, FirstName,LastName
Audit | AuditCompare | DataMenu | CID
Audit | AuditCompare | Reporting | ProjectStats
Shipping |  | Reporting | ProjectStats
Shipping |  | Inquiry Posting | shipping Population
InquiryPosting |  | Reporting | ProjectStats
IZ |  | Reporting | ProjectStats
tokenizes files |  | InputProcess | need tokenization
TOK |  | Reporting | ProjectStats
Stacking |  | Operation